## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | BE-001 | As a user, input my financial details so that the system can analyze my loan eligibility | MUST HAVE |  | Nistha Hooda | 3- Completed
S1 | S1 | BE-002 | As a system, to preprocess customer data to extract key financial features. | MUST HAVE | FE-009 | Harini Gompa | 3- Completed
S1 | S1 | BE-003 | As a dev, build an NLP module to understand user queries. | MUST HAVE | FE-011 | Sai Ganesh | 3- Completed
S2 | S2 | BE-004 | As a system, to classify loan eligibility using ML models. | MUST HAVE | FE-011 | Harika Devoju | 3- Completed
S2 | S2 | BE-005 | As a user, to receive a recommended loan amount based on my eligibility. | MUST HAVE |  | Shreya Kumari | 3- Completed
S2 | S2 | BE-006 | As a system, to store user interaction logs for auditing. | MUST HAVE | FE-007, FE-014 | Mohit Kumar | 3- Completed
S2 | S2 | BE-007 | As a dev, to integrate the system with a database to store user profiles. | MUST HAVE | FE-015 | Souhardya Sikder | 3- Completed
S2 | S2 | BE-008 | As a user, a simple dashboard to view eligibility results. | MUST HAVE | FE-017 | Shanmukh Singhaampalli | 3- Completed
S2 | S2 | BE-009 | As a system, to generate a summary report explaining approval/rejection reasons. | MUST HAVE | FE-010 | Kanishka, Aditi Das | 3- Completed
S2 | S2 | BE-010 | As a dev, to deploy the AI advisory system for public use. | MUST HAVE |  | Menmathi | 3- Completed
Note on F1: ====== ID#AAABYLGvqXM Sumeet Kumar Barua08 (2024-11-14 13:03:52) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 37.5 | 3 | 5 | 4 | 3.5 | 4 | 2 | 1 | 3 | 2.5 | 2.5 | 1 | 1 | 1 | 1
SPRINT 1 BACKLOG
BE-001 | TASK-001 | Introduction of the project | 2025-10-15 | 2025-10-20 | Mohit Kumar | Project Overview | Completed | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BE-002 | TASK-002 | SQL and Python task completation | 2025-10-21 | 2025-10-26 | Mohit Kumar | Backend Setup | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BE-003 | TASK-003 | AI and ML Model Research part done | 2025-10-26 | 2025-11-05 | Mohit Kumar | AI/ ML Research | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
BE-001 | TASK-001 | Handle missing values, encode categorical variables, normalize features | 2025-10-15 | 2025-10-18 | Harika Devoju | Dataset Cleaning | Completed | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BE-002 | TASK-002 | Configure OCR to read pay slips, bank statements, tax forms | 2025-10-19 | 2025-10-22 | Kanishka | Document OCR Setup | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
BE-003 | TASK-003 | Train model to detect document type | 2025-10-23 | 2025-10-26 | Sai Ganesh | Document Classification Model | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
BE-004 | TASK-004 | Implement rules for validating extracted numeric fields | 2025-10-27 | 2025-10-30 | Shanmukh singampalli | Data Validation Rules | Completed | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0
BE-005 | TASK-005 | Create uniform data structure for the pipeline | 2025-10-31 | 2025-11-03 | Souhardyo Sikder | Dataset Schema Standardization | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
SPRINT 3 BACKLOG
BE-006 | TASK-001 | Build and train model to understand user loan-related queries. | 2025-11-04 | 2025-11-05 | Shanmukh singampalli | NLP Intent Detection Model | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BE-007 | TASK-002 | Extract key fields: income, loan amount, tenure, employment type, credit score. | 2025-11-06 | 2025-11-07 | Shreya Kumari | Entity Extraction Pipeline | Completed | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BE-008 | TASK-003 | Perform text cleaning: stopwords removal, stemming, lemmatization. | 2025-11-08 | 2025-11-09 | Nistha Hooda | Tokenization & Text Preprocessing | Completed | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BE-009 | TASK-004 | Create features: DTI, EMI ratio, credit brackets, income categories. | 2025-11-10 | 2025-11-11 | Harini Gompa | Feature Engineering | Completed | 1.5 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BE-010 | TASK-005 | Integrate voice input using speech-to-text API. | 2025-11-12 | 2025-11-13 | Mohit Kumar | Speech-to-Text Integration | Completed | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BE-011 | TASK-006 | Categorize queries: eligibility, document upload, repayment, loan amount inquiries. | 2025-11-14 | 2025-11-15 | Souhardyo Sikder | User Query Classification | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BE-012 | TASK-007 | Apply normalization and scaling to numerical features. | 2025-11-16 | 2025-11-17 | Menmathi | Feature Scaling & Normalization | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BE-013 | TASK-008 | Integrate the OCR service into the /upload API endpoint. | 2025-11-18 | 2025-11-19 | Harini Gompa | NLP Testing & Accuracy Evaluation | Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
BE-014 | TASK-001 | Train machine learning model on cleaned dataset for eligibility prediction. | 2025-11-20 | 2025-11-23 | Nistha Hooda | ML Model Training | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BE-015 | TASK-001 | Improve model accuracy using tuning methods (Grid Search / Random Search). | 2025-11-24 | 2025-11-26 | Menmathi | Hyperparameter Tuning | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BE-016 | TASK-002 | Evaluate model performance using accuracy, precision, recall, and ROC-AUC. | 2025-11-27 | 2025-11-29 | Aditi Das | Model Evaluation | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 5 BACKLOG
BE-017 | TASK-001 | Implement automated loan compliance checks based on lending regulations. | 2025-11-30 | 2025-12-03 | Shreya Kumari | Compliance Rule Integration | Completed | 10 | 1 | 2 | 3 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BE-018 | TASK-002 | Develop logic to output eligibility decision + recommended loan amount. | 2025-12-04 | 2025-12-09 | Mohit Kumar | Decision Recommendation Logic | Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 1 | 1
Note on U3: ====== ID#AAABYLHdiCo Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 12 work
Note on N3: ====== ID#AAABYLHdiCs Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 5 work
Note on J3: ====== ID#AAABYLHdiCk Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 1 work
Note on R3: ====== ID#AAABYLGvqX8 Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 9 work
Note on K3: ====== ID#AAABYLGvqX4 Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 2 work
Note on V3: ====== ID#AAABYLGvqX0 Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 13 work
Note on Q3: ====== ID#AAABYLGvqXw Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 8 work
Note on M3: ====== ID#AAABYLGvqXs Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 4 work
Note on P3: ====== ID#AAABYLGvqXo Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 7 work
Note on D2: ====== ID#AAABYLGvqXg Please enter the dates in either of these formats (2024-11-14 13:03:52) 9/15/2016 or 15-Sep-2016
Note on T3: ====== ID#AAABYLGvqXc Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 11 work
Note on O3: ====== ID#AAABYLGvqXY Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 6 work
Note on W3: ====== ID#AAABYLGvqXk Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 14 work
Note on L3: ====== ID#AAABYLGvqXU Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 3 work
Note on I3: ====== ID#AAABYLGvqXQ Sumeet Kumar Barua08 (2024-11-14 13:03:52) This is the total task estimated in hours for all the user stories
Note on E2: ====== ID#AAABYLGvqXI Please enter the dates in either of these formats (2024-11-14 13:03:52) 9/15/2016 or 15-Sep-2016
Note on S3: ====== ID#AAABYLGvqXE Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 10 work

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 2025-10-19 | 2025-10-26 | Mohit | Begin organizing and cleaning user financial data for accurate ML training. | Avoid manually entering sample data without validation. | Consistent documentation of model requirements and system flow. | Implemented a preprocessing module and added validation checks for income, credit score, liabilities, and employment details.
2 | S2 | 2025-10-27 | 2025-11-05 | Mohit | Start integrating the ML model into the backend decision engine. | storing logs in temporary files without structure. | testing each API endpoint with sample user input. | Connected ML model to backend APIs and implemented structured logging for user queries and model outputs.
3 | S3 | 2025-11-06 | 2025-11-15 | Mohit | Begin building the user dashboard for loan eligibility results. | using direct SQL queries without optimization. | maintaining error logs for debugging. | A clean UI dashboard was developed, and indexing was added to database tables to improve load times.
4 | S4 | 2025-11-16 | 2025-11-29 | Mohit | Start preparing the deployment pipeline and environment setup. | testing manually; move to automated testing for faster iteration. | refining accuracy and transparency of the loan recommendation logic. | Deployment environment configured, and an explainability module was added to show loan approval/rejection reasons.

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 | Day 3 | OCR still misreads a few document types | Retrained OCR/document classifier
S2 | Day 12 | NLP intent detection inconsistent | Enhanced NLP pipeline
S3 | Day 20 | Model accuracy fluctuates due to imbalance | Applied data balancing techniques
S3 | Day 25 | Limited real-world-like test data | Added synthetic/anonymized data
S4 | Day 50 | Slow system response time | Optimized backend performance